## Sheet1
Daily Report (March 2016)
Name: Balderas, John Paul
Designation: Software Specialist
2016-03-10 | Project | Client | Activities | Duration (Hours) | Remarks
Today's Activities | HRIS v2 | Inhouse | Finished Employee Education module | 2
| HRIS v2 | Inhouse | Finished Employee Skills module | 2
| HRIS v2 | Inhouse | Finished Employee Employment History module | 4
Tomorrow's Activities | HRIS v2 | Inhouse | Finish Employee Files | 2
| HRIS v2 | Inhouse | Start development of Time in / Time out module | 6
2016-03-09 | Project | Client | Activities | Duration (Hours) | Remarks
Today's Activities | HRIS v2 | Inhouse | Finished Employee List | 2
| HRIS v2 | Inhouse | Finished Updating of Employee Personal Information | 5
| HRIS v2 | Inhouse | Started on Employee Education | 1
Tomorrow's Activities | HRIS v2 | Inhouse | Create Employee Education module | 2
| HRIS v2 | Inhouse | Create Employee Skills module | 2
| HRIS v2 | Inhouse | Create Employee Employment History module | 4
2016-03-08 | Project | Client | Activities | Duration (Hours) | Remarks
Today's Activities | HRIS v2 | Inhouse | Finish Use Case Scenarios | 2
| HRIS v2 | Inhouse | Prepare template to be used for UI | 2
| HRIS v2 | Inhouse | Start Development of Employee Personal Information | 4
Tomorrow's Activities | HRIS v2 | Inhouse | Employee List | 2
| HRIS v2 | Inhouse | Employee Personal Information | 2
| HRIS v2 | Inhouse | Employee Skills | 4
2016-03-07 | Project | Client | Activities | Duration (Hours) | Remarks
Today's Activities | HRIS v2 | Inhouse | Created Use Case Scenarios | 7
| HRIS v2 | Inhouse | Modified Database Schema | 0.5
| HRIS v2 | Inhouse | Created Business cards Jay Masangcal | 0.5
Tomorrow's Activities | HRIS v2 | Inhouse | Finish Use Case Scenarios | 2
| HRIS v2 | Inhouse | Prepare template to be used for UI | 2
| HRIS v2 | Inhouse | Start Development of Employee Personal Information | 4
2016-03-04 | Project | Client | Activities | Duration (Hours) | Remarks
Today's Activities | HRIS v2 | Inhouse | Modified Database Schema | 1
| HRIS v2 | Inhouse | Planning and discussion of functions with PRODCOM | 6
| HRIS v2 | Inhouse | Created Gant Chart for development | 1
Tomorrow's Activities | HRIS v2 | Inhouse | Modify Database Schema | 1
| HRIS v2 | Inhouse | Get Types of Leaves | 0.5
| HRIS v2 | Inhouse | Development | 6.5
2016-03-03 | Project | Client | Activities | Duration (Hours) | Remarks
Today's Activities | HRIS | Inhouse | Finished Absent List Report | 1.5
| HRIS v2 | Inhouse | Listed HRIS Functions | 1.5
| HRIS v2 | Inhouse | Created Database Schema | 5
Tomorrow's Activities | HRIS v2 | Inhouse | Planning and documentation | 8
2016-03-02 | Project | Client | Activities | Duration (Hours) | Remarks
Today's Activities | HRIS | Inhouse | Finished Flexitime DTR Report | 7
| HRIS | Inhouse | Started on the Absent List Report | 0.5
| HRIS | Inhouse | Modified Attendance Summary Report | 0.25
| HRIS | Inhouse | Added undertime to Attendance Summary Report | 0.25
Tomorrow's Activities | HRIS | Inhouse | Validate data of the reports | 4
| HRIS | Inhouse | Update the current system | 2
| HRIS | Inhouse | Generate Attendance Summary Report | 2
2016-03-01 | Project | Client | Activities | Duration (Hours) | Remarks
Today's Activities | HRIS | Inhouse | Added rest day and absent management functions | 1
| HRIS | Inhouse | Created SQL Query to be used for the Attendance Summary Report | 2
| HRIS | Inhouse | Created Attendance Summary Report | 4
| HRIS | Inhouse | Started on the modification of the Attendance Report | 1
Tomorrow's Activities | HRIS | Inhouse | Continue modification of the Attendance Report | 8